## Folha1
Task | Priority (1 - High; 2 - Medium; 3 - Low) | Owner | Status (Done, Discarded, TBD, Wish) | Deadline | Type | Description
Lidar com pop-up menu após chamada (só vodafone?) | 1 |  | TBD |  | new functionality
Always visible | 1 |  | TBD |  | new functionality | what if other activity from another app shows up?
Debug todas as combinações de fazer chamada | 2 | Hugo | TBD |  | debug
Usar lista de contactos em incoming call | 3 |  | TBD |  | new functionality
Aplicar earcons | 3 | Hugo | Done |  | new functionality | Earcons em acções de select e voltar
TTS Spell | 3 | Hugo | Done |  | new functionality
Lidar com numero privado (incoming number = null) | 3 | Hugo | Done |  | new functionality
Menu Manager Singleton | 2 | Hugo | Done |  | Modification | Reuse code
No segundo ciclo de leitura não permite escolha da ultima opção | 1 | Hugo | Done |  | bug
Allow option selection while reading title | 1 | Hugo | Done |  | modification
Full screen | 1 | Hugo | Done |  | modification
Debug todas as combinações de receber chamada / em chamada | 2 | Hugo | Done